## Sheet1
Week | W/C Sat | Major Task | Task Duration (Hours) | Date Completed
1 | 2017-01-28 | TM470 Module Website Review | 4 | 2017-01-29
|  | Meeting With Client Stakeholder | 1 | 2017-02-03
2 | 2017-02-04 | Introductory Email To Tutor | 3 | 2017-02-05
|  | Set Up Project Log Sheets | 2 | 2017-02-06
3 | 2017-02-11 | Project Outline Tutor Group Forum Posting | 4 | 2017-02-12
|  | Summary Email To Tutor | 1 | 2017-02-14
|  | Meeting With Client Stakeholder | 1 | 2017-02-17
4 | 2017-02-18 | Evaluate Lifecycle Models & Make Choice | 2 | 2017-02-19
|  | Create Detailed Project Plan | 10 | 2017-02-20
|  | Review Detailed Project Plan | 3 | 2017-02-21
|  | Summary Email To Tutor | 2 | 2017-02-22
|  | Write Initial Problem Statement | 2 | 2017-02-23
|  | Meeting With Client Stakeholder | 1 | 2017-02-24
5 | 2017-02-25 | Prepare Literature Search And Review Literature | 2 | 2017-02-26
|  | Evaluate Resources, Skills & Methods Needed For Project | 2 | 2017-02-26
|  | Complete TMA01 - Deadline 28/02/2017 | 15 | 2017-02-27
|  | Literature Review | 4 | 2017-03-03
6 | 2017-03-04 | Review & Elaborate Problem Statement | 3 | 2017-03-05
|  | Record Important Business Rules | 1 | 2017-03-05
|  | Meeting With Client Stakeholder | 1 | 2017-03-06
|  | Revise Problem Statement | 1 | 2017-03-06
|  | Revise Business Rules | 1 | 2017-03-06
7 | 2017-03-11 | Summary Email To Tutor | 2 | 2017-03-13
|  | Literature Review | 3 | 2017-03-14
|  | Create Domain Structural Model | 4 | 2017-03-15
|  | Meeting With Client Stakeholder | 1 | 2017-03-16
|  | Create Use Case Model | 5 | 2017-03-17
8 | 2017-03-18 | Literature Review | 3 | 2017-03-19
|  | Literature Review | 2 | 2017-03-24
9 | 2017-03-25 | Literature Review | 2 | 2017-03-25
|  | Literature Review | 3 | 2017-03-26
10 | 2017-04-01 | Revise Project Plan | 4 | 2017-04-01
|  | Summary Email To Tutor | 1 | 2017-04-02
|  | Elaborate Use Cases | 4 | 2017-04-04
|  | Telephone Call With Tutor | 1 | 2017-04-05
|  | Meeting With Client Stakeholder | 1 | 2017-04-07
|  | Capture Requirements On Volere Template | 3 | 2017-04-07
|  | Prioritise Requirements | 1 | 2017-04-07
11 | 2017-04-08 | Check Installation Of NetBeans & Review Functionality | 2 | 2017-04-08
|  | Literature Review | 5 | 2017-04-09
|  | Choose Software Architecture | 2 | 2017-04-10
|  | Review Project Artefacts Produced | 1 | 2017-04-11
|  | Review Progress | 1 | 2017-04-11
|  | Start TMA02 | 5 | 2017-04-14
12 | 2017-04-15 | Complete TMA02 - Deadline 19/04/2017 | 30 | 15/04/2017 to 19/04/2017
|  | Create Analysis Structural Model | 4 | 2017-04-21
13 | 2017-04-22 | Create Design Structural Model | 4 | 2017-04-23
|  | Literature Review | 2 | 2017-04-24
14 | 2017-04-29 | Literature Review | 2 | 2017-04-30
|  | Literature Review | 2 | 2017-05-01
15 | 2017-05-06 | Literature Review | 2 | 2017-05-03
|  | Literature Review | 2 | 2017-05-07
16 | 2017-05-13 | Create Behavioural Models | 4 | 2017-05-14
|  | Summary Email To Tutor | 1 | 2017-05-17
|  | Code Skeleton Classes Of Business Layer Prototype Package | 5 | 2017-05-19
|  | Review Skeleton Architecture Of Business Layer Prototype Package | 2 | 2017-05-19
17 | 2017-05-20 | Code Class Composition Relationships Using Collections Classes | 3 | 2017-05-20
|  | Code Class Constructors And Helper Methods | 3 | 2017-05-20
|  | Test Class Construction For Business Layer Classes | 2 | 2017-05-20
|  | Code Class Associations, Navigability And Constraints | 4 | 2017-05-21
|  | Test Class Associations, Navigability And Constraints For Business Layer Classes | 1 | 2017-05-21
|  | Summary Email To Tutor | 1 | 2017-05-24
|  | Telephone Call With Tutor | 1 | 2017-05-25
|  | Code And Test Implementation Of "Add Player" Use Case In Business Layer | 2 | 2017-05-26
|  | Design Overall Structure Of UI Prototype Package | 3 | 2017-05-26
18 | 2017-05-27 | Design "Add Player" Use Case Tabbed Pane For UI Layer | 5 | 2017-05-27
|  | Code "Add Player" Button Functionality For UI Layer | 4 | 2017-05-27
|  | Test Functionality Of "Add Player" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-05-27
|  | Code And Test "Clear Screen" Button Functionality (On "Add Player" Pane) For UI Layer | 2 | 2017-05-28
|  | Design "View/Amend Player" Use Case Tabbed Pane For UI Layer | 3 | 2017-05-28
|  | Code And Test Implementation Of "View Player" And "Amend Player" Use Cases In Business Layer | 3 | 2017-05-28
|  | Code "View Player" Button Functionality For UI Prototype | 4 | 2017-05-29
|  | Test Functionality Of "View Player" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-05-29
|  | Code "Amend Player" Button Functionality For UI Layer | 4 | 2017-05-29
|  | Test Functionality Of "Amend Player" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-05-29
|  | Code And Test Implementation Of "Delete Player" Use Case In Business Layer | 1 | 2017-05-30
|  | Code "Delete Player" Button Functionality (On "View/Amend Player" Pane) For UI Layer | 1 | 2017-05-30
|  | Test Functionality Of "Delete Player" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-05-30
19 | 2017-06-03
Project Pause Due To Personal Circumstances
20 | 2017-06-10 | Revise Project Plan | 3 | 2017-06-11
|  | Summary Email To Tutor | 2 | 2007-06-14
21 | 2017-06-17
Project Pause Due To Personal Circumstances
22 | 2017-06-24 | Design "View Player List" Use Case Tabbed Pane For UI Prototype | 1 | 2017-06-25
|  | Code And Test Implementation Of "View Player List" Use Case In Business Layer | 3 | 2017-06-25
|  | Code "View Player List" Button Functionality For UI Prototype | 1 | 2017-06-25
|  | Test Functionality Of "View Player List" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-06-25
|  | Revise Project Plan | 1 | 2017-06-27
|  | Summary Email To Tutor | 1 | 2017-07-02
23 | 2017-07-01
Holiday
24 | 2017-07-08
Project Pause Due To Personal Circumstances
25 | 2017-07-15 | Review Project Artefacts Produced | 2 | 2017-07-17
|  | Review Progress | 2 | 2017-07-17
|  | Start TMA03 | 30 | 17/07/2017 to 19/07/2017
|  | Complete TMA03 - Deadline 21/07/2017 | 4 | 2017-07-20
26 | 2017-07-22
Project Pause Due To Personal Circumstances
27 | 2017-07-29 | Revise Project Plan | 2 | 2017-08-01
|  | Literature Review | 4 | 2017-08-02
|  | Code Persistence Of First Evolutionary System Prototype Using Object Serialisation In Business Layer | 1 | 2017-08-03
|  | Code Persistence Of UI Prototype Using Object Input/Output Streams For Open And Save File Menu Items | 3 | 2017-08-03
|  | Test Functionality Of Persistence Integrated Between Business Layer & UI Layer | 2 | 2017-08-04
|  | Refactor And Test "Add Player" Use Case In Business Layer To Solve Class Variable Persistence Issue | 2 | 2017-08-04
28 | 2017-08-05 | Evaluate First Evolutionary System Prototype With Client Stakeholder | 3 | 2017-08-05
|  | Deploy And Test First Evolutionary System Prototype With Client Stakeholder | 3 | 2017-08-05
|  | Prioritise Requirements And Use Cases For Second Evolutionary System Prototype | 2 | 2017-08-06
|  | Review Existing Analysis & Design Structural Models | 1 | 2017-08-06
|  | Review Existing Behavourial Models | 1 | 2017-08-06
|  | Create NetBeans Project For Second Evolutionary System Prototype By Reusing First Prototype Project | 1 | 2017-08-06
|  | Code And Test Implementation Of "Add Fixture" Use Case In Business Layer | 2 | 2017-08-06
|  | Design "Add Fixture" Use Case Tabbed Pane For UI Layer | 1 | 2017-08-06
|  | Code "Add Fixture" Button Functionality For UI Layer | 1 | 2017-08-06
|  | Test Functionality Of "Add Fixture" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-08-06
29 | 2017-08-12 | Design "View Fixture List" Use Case Tabbed Pane For UI Layer | 1 | 2017-08-12
|  | Code And Test Implementation Of "View Fixture List" Use Case In Business Layer | 1 | 2017-08-12
|  | Code "View Fixture List" Button Functionality For UI Layer | 1 | 2017-08-12
|  | Test Functionality Of "View Fixture List" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-08-12
|  | Design "View/Amend Fixture" Use Case Tabbed Pane For UI Layer | 3 | 2017-08-12
|  | Code And Test Implementation Of "View Fixture" And "Amend Fixture" Use Cases In Business Layer | 2 | 2017-08-13
|  | Code "View Fixture" Button Functionality For UI Layer | 1 | 2017-08-13
|  | Test Functionality Of "View Fixture" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-08-13
|  | Code "Amend Fixture" Button Functionality For UI Layer | 1 | 2017-08-13
|  | Test Functionality Of "Amend Fixture" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-08-13
|  | Code And Test Implementation Of "Delete Fixture" Use Case In Business Layer | 1 | 2017-08-13
|  | Code "Delete Fixture" Button Functionality (On "View/Amend Fixture" Pane) For UI Layer | 1 | 2017-08-13
|  | Test Functionality Of "Delete Fixture" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-08-13
30 | 2017-08-19 | Code And Test "Add Available Player" Button Functionality (On "View/Amend Fixture Pane") For UI Layer | 2 | 2017-08-20
|  | Code And Test "Remove Available Player" Button Functionality (On "View/Amend Fixture Pane") For UI Layer | 2 | 2017-08-20
|  | Code And Test "Add Selected Player" Button Functionality (On "View/Amend Fixture Pane") For UI Layer | 2 | 2017-08-21
|  | Code And Test "Remove Selected Player" Button Functionality (On "View/Amend Fixture Pane") For UI Layer | 2 | 2017-08-21
|  | Code And Test "View Fixture Availability" Button Functionality (On "View/Amend Player" Pane) For UI Layer | 1 | 2017-08-21
|  | Code And Test "View Fixture Selection" Button Functionality (On "View/Amend Player" Pane) For UI Layer | 1 | 2017-08-21
|  | Summary Email To Tutor | 1 | 2017-08-22
|  | Refactor And Test "Delete Player" Use Case In Business Layer Ensuring All References To Object Are Removed | 2 | 2017-08-22
|  | Refactor And Test "Delete Fixture" Use Case In Business Layer Ensuring All References To Object Are Removed | 1 | 2017-08-22
|  | Design "Add Fixture Results" Use Case Tabbed Pane For UI Layer | 5 | 2017-08-23
|  | Code And Test Implementation Of "Add Fixture Results" Use Case In Business Layer | 1 | 2017-08-24
|  | Code "Amend Fixture Result" Button Functionality For UI Layer | 1 | 2017-08-24
|  | Test Functionality Of "Add Fixture Results" Use Case Integrated Between Business Layer & UI Layer | 1 | 2017-08-24
|  | Literature Review | 2 | 2017-08-24
|  | Revise Project Plan | 3 | 2017-08-25
|  | Literature Review | 2 | 2017-08-25
|  | Summary Email To Tutor | 1 | 2017-08-27
31 | 2017-08-26
Project Pause Due To Personal Circumstances
32 | 2017-09-02 | Evaluate Second Evolutionary System Prototype With Client Stakeholder | 3 | 2017-09-02
|  | Deploy And Test Second Evolutionary System Prototype With Client Stakeholder | 2 | 2017-09-02
|  | Start EMA | 4 | 2017-09-02
|  | Work On EMA | 6 | 2017-09-03
|  | Work On EMA | 2 | 2017-09-04
|  | Work On EMA | 2 | 2017-09-05
|  | Work On EMA | 8 | 2017-09-06
|  | Work On EMA | 8 | 2017-09-07
|  | Work On EMA | 8 | 2017-09-08
33 | 2017-09-09 | Work On EMA | 8 | 2017-09-09
|  | Complete EMA - Deadline 11/09/2017 | 8 | 2017-09-10

## Sheet2
TM470
JAMES BISWELL
Y3258789
Project Plan For The Design & Development
Of A Player & Fixture Management System
For Long Marston Cricket Club
Legend
Project Phases:
Choosing Project Title & Topic
Scoping & Defining Project
Project Planning
Researching Project Subject Area
Analysing Problem To Be Addressed
Conducting Project
Evaluating Results Of Project
Evaluating Conduct Of Project
Producing Final Report On Project
Unified Process Iterative & Incremental
Sofware Development Disciplines:
Business Modelling
Requirements
Analysis & Design
Implementation
Testing
Project Management
Deployment